## Dashboard
🏨 Fairfield Maintenance Command Center
Real-time operations dashboard · Work Orders · PM Schedules · Parts Inventory · Facility Health
🎟️ Open Tickets | 33 |  | Work Order Status |  | Open WOs by Priority
🏠 Rooms w/ Open WOs | 20 |  | Not Started | 29 | 🚨 Critical | 28
⚠️ PMs Overdue | 0 |  | Work In Progress | 4 | 🔴 High | 29
📦 Parts to Reorder | 0 |  | Completed | 63 | 🟡 Medium | 19
[5 empty] | 🟢 Low | 21
🚨 Critical & High Priority Open Work Orders | [6 empty] | 🔔 Upcoming PM — Due Within 7 Days
Room / Location | Issue Type | Priority |  |  |  |  | Room / Space | Performed By | Last PM Date | Next Due Date | Days Remaining | PM Status
201 | Electrical | Critical
209 | Doors | Critical
219 | Doors | Critical
303 | Doors | Critical
304 | Safety | Critical
Work Orders – Last 30 Days by Issue Type
Issue Type | Count
Misc. | 5
Climate/AC | 5
Electrical | 4
Technology | 15
Plumbing | 15
Walls | 18
Ceiling | 3
Floors | 15
Doors | 13
Safety | 4

## Active Work Orders
Active Work Orders
Track guest- or staff-reported issues that need immediate attention and follow-up.
Ticket ID | Room/Location | Issue Type | Issue Description | Priority | Date Reported | Status
WO-001 | 213 | Plumbing | Flushmate toilet system leaking full replacement needed. | Critical | 2026-07-13 12:33 | Completed
WO-002 | 313 | Plumbing | Flushmate toilet system leaking full replacement needed. | Critical | 2026-07-13 13:51 | Completed
WO-003 | Other | Misc. | One of the belts on the vacuum for housekeeping broke needs to be replaced | Medium | 2026-07-15 09:30 | Completed
WO-005 | 210 | Floors | Doorstop is broken or off. | Low | 2026-07-17 | Completed
WO-009 | 219 | Ceiling | Water from 319s plumbing issue is leaking from the ceiling down onto everything. | Medium | 2026-07-17 14:30 | Completed
WO-011 | 121 | Technology | TV volume is not working. | Low | 2026-07-19 09:08 | Completed
WO-012 | 419 | Misc. | There seems to be an unusual amount of bugs in the room. | Critical | 2026-07-19 09:22 | Completed
WO-013 | 215 | Electrical | Refrigerator not working properly | High | 2026-07-19 11:05 | Completed
WO-014 | 107 | Floors | Carpet needs to be Shampooed | High | 2026-07-19 11:21 | Completed
WO-015 | 303 | Doors | The shower door stopped needs to be adjusted | Low | 2026-07-19 12:25 | Completed
WO-017 | 310 | Floors | Condensation from the a c is soaking the floor | Critical | 2026-07-19 14:18 | Completed
WO-012 | 205 | Plumbing | lever to turn on shower isn't working. | High | 2026-07-20 10:38 | Completed
WO-013 | 217 | Plumbing | lever to turn on shower isn't working. | High | 2026-07-20 10:58 | Completed
WO-014 | 411 | Doors | battery dead door will not open | Critical | 2026-07-20 09:40 | Completed
WO-015 | 319 | Floors | room smells, fishy smell. Ozone machine and shampoo carpet. | High | 2026-07-20 11:34 | Completed
WO-016 | 208 | Plumbing | toilet is making a weird sound. | Medium | 2026-07-20 13:10 | Completed
WO-017 | 211 | Misc. | Bugs in the room guest moved. | Critical | 2026-07-21 07:31 | Completed
WO-018 | 317 | Technology | TV is not working properly. | Medium | 2026-07-21 10:27 | Completed
WO-019 | 211 | Floors | Stains on floor, shampoo needed. | Medium | 2026-07-21 11:38 | Completed
WO-020 | 410 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-21 12:55 | Completed
WO-021 | 101 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-23 09:04 | Completed
WO-022 | 107 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-23 09:58 | Completed
WO-023 | 410 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-23 10:58 | Completed
WO-024 | 202 | Plumbing | Sink isn't draining water. | High | 2026-07-23 12:16 | Completed
WO-025 | 215 | Climate/AC | Noise/Crickets in the AC. | Medium | 2026-07-23 12:45 | Completed
WO-026 | Other | Plumbing | Employee toilet needs to be repaired. | Critical | 2026-07-24 09:25 | Completed
WO-027 | 211 | Walls | Reattach the bodywash holder. | Low | 2026-07-24 10:44 | Completed
WO-028 | 310 | Floors | Water from AC needed to be shampooed up. | Low | 2026-07-24 12:15 | Completed
WO-029 | 319 | Floors | Soda spilled carpet needs shampooed | Medium | 2026-07-24 15:29 | Completed
WO-030 | 211 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-25 10:15 | Completed
WO-031 | 201 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-25 10:29 | Completed
WO-032 | 203 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-25 10:55 | Completed
WO-033 | 410 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-25 11:28 | Completed
WO-034 | 310 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-25 12:00 | Completed
WO-035 | 315 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-25 12:23 | Completed
WO-036 | 413 | Doors | Dead battery door locked out. | Critical | 2026-07-25 12:51 | Completed
WO-037 | 101 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-25 13:03 | Completed
WO-038 | 219 | Ceiling | Water leaking from ceiling. | Critical | 2026-07-25 14:25 | Completed
WO-039 | 415 | Doors | Replaced door battery to prevent lockout. | Critical | 2026-07-25 14:50 | Completed
WO-040 | 101 | Doors | Replaced door battery to prevent lockout. | Critical | 2026-07-25 15:14 | Completed
WO-041 | 107 | Doors | Replaced door battery to prevent lockout. | Critical | 2026-07-25 15:46 | Completed
WO-042 | 303 | Technology | TV not working properly. | Medium | 2026-07-26 08:52 | Completed
WO-043 | 319 | Plumbing | Toilet needs further adjustment. | Critical | 2026-07-26 11:13 | Completed
WO-044 | 319 | Floors | Caulk the seal around the toilet. | Critical | 2026-07-26 12:50 | Completed
WO-045 | 215 | Plumbing | Adjust toilet so it stops flushing on its own. | High | 2026-07-26 13:05 | Completed
WO-046 | Other | Misc. | Fridge in dining area needs to be unlocked. | Medium | 2026-07-26 13:48 | Completed
WO-047 | 105 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-26 14:15 | Completed
WO-048 | 121 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-27 09:02 | Completed
WO-049 | 318 | Floors | Doorstop needs to be adjusted. | Low | 2026-07-27 13:53 | Completed
WO-050 | 203 | Floors | Carpet needs to be Shampooed | Medium | 2026-07-28 13:13 | Completed
WO-051 | 413 | Climate/AC | AC cleaned and drained. | High | 2026-07-28 13:13 | Completed
WO-052 | 215 | Ceiling | Water leaking from ceiling. | High | 2026-07-28 13:13 | Completed
WO-053 | 104 | Plumbing | Loose toilet seat. | Low | 2026-07-30 10:38 | Completed
WO-054 | 107 | Walls | Mold clean up. | High | 2026-07-30 10:54 | Completed
WO-055 | 210 | Floors | Bathroom doorstop adjusted and fixed. | Medium | 2026-07-30 13:16 | Completed
WO-056 | 307 | Floors | Carpet needs to be Shampooed | High | 2026-07-30 16:51 | Completed
WO-057 | 313 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-31 10:31 | Completed
WO-058 | 317 | Plumbing | Shower switch fixed. | Medium | 2026-07-31 11:55 | Completed
WO-059 | 317 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-31 11:55 | Completed
WO-060 | 101 | Walls | Curtain needs to be reattached/adjusted. | Low | 2026-07-31 14:07 | Completed
WO-061 | 219 | Misc. | Ozone machine placed for weird smell. | Low | 2026-07-31 15:20 | Completed
WO-062 | 210 | Floors | Carpet needs to be Shampooed | High | 2026-07-31 16:04 | Completed
WO-004 | 207 | Walls | The holder for the conditioner needs to be reattached. | Low | 2026-07-17 | Not Started
WO-006 | 210 | Electrical | Outlet needs to be replaced. | High | 2026-07-17 11:30 | Not Started
WO-007 | 210 | Floors | Grout and Silicone need to be reapllied. | High | 2026-07-17 11:30 | Not Started
WO-008 | 210 | Walls | Silicone needs to be reapplied on the shower walls. | High | 2026-07-17 11:30 | Not Started
WO-067 | 316 | Electrical | Refrigerator not working properly. | High | 2026-07-20 08:04 | Not Started
WO-068 | 101 | Plumbing | Showerhead is leaking from the side. | High | 2026-07-20 08:05 | Not Started
WO-069 | 201 | Electrical | Thermostat shorted, condensation/water coming from hole in wall that feeds power to it. | Critical | 2026-07-23 10:15 | Not Started
WO-070 | 209 | Climate/AC | Thermostat needs to be replaced/repair to figure out the control issue with AC | High | 2026-07-26 09:28 | Not Started
WO-055 | 209 | Doors | Need to replace door battery to prevent lockout. | Critical | 2026-07-26 09:30 | Not Started
WO-072 | 219 | Doors | Need to replace door battery to prevent lockout. | Critical | 2026-07-26 09:41 | Not Started
WO-073 | 303 | Doors | Need to replace door battery to prevent lockout. | Critical | 2026-07-26 09:54 | Not Started
WO-074 | 304 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-26 09:58 | Not Started
WO-075 | 304 | Safety | Window lock missing, need to install. | Critical | 2026-07-26 10:00 | Not Started
WO-076 | 306 | Doors | Need to replace door battery to prevent lockout. | Critical | 2026-07-26 10:06 | Not Started
WO-077 | 306 | Safety | Window lock missing, need to install. | Critical | 2026-07-26 10:07 | Not Started
WO-078 | 314 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-26 10:09 | Not Started
WO-079 | 318 | Plumbing | Multiple spots in bathroom need to be recaulked. | Medium | 2026-07-26 10:12 | Not Started
WO-080 | 318 | Safety | Window lock missing, need to install. | Critical | 2026-07-26 10:12 | Not Started
WO-081 | 402 | Doors | Need to replace door battery to prevent lockout. | Critical | 2026-07-26 10:15 | Not Started
WO-082 | 402 | Technology | Tv data cable replaced to fix TV not turning off. | High | 2026-07-26 10:15 | Not Started
WO-083 | 402 | Walls | Towel hanger behind door in bathroom needs adjustment. | Low | 2026-07-26 10:15 | Not Started
WO-084 | 319 | Doors | Need to replace door battery to prevent lockout. | Critical | 2026-07-26 12:55 | Not Started
WO-085 | 206 | Plumbing | Multiple spots in bathroom need to be recaulked. | Medium | 2026-07-26 14:36 | Not Started
WO-086 | 105 | Doors | Need to replace door battery to prevent lockout. | Critical | 2026-07-26 14:39 | Not Started
WO-087 | 105 | Safety | Window lock missing, need to install. | Critical | 2026-07-26 14:39 | Not Started
WO-088 | Other | Walls | Need Several cosmetic fixes in the fitness center. | Medium | 2026-07-27 16:26 | Not Started
WO-089 | 210 | Walls | Window seal needs to be redone it is cracked. | Medium | 2026-07-30 13:45 | Not Started
WO-090 | 202 | Walls | Window seal needs to be redone it is cracked. | Medium | 2026-07-30 14:20 | Not Started
WO-010 | 319 | Plumbing | Toilet is leaking, repaired | High | 2026-07-17 14:30 | Work In Progress
WO-016 | 310 | Climate/AC | The air conditioner is not draining condensation properly | Critical | 2026-07-19 14:18 | Work In Progress | Currently the first layer of mud and tap are applied, waiting on materials to continue
WO-093 | 413 | Climate/AC | The air conditioner is not draining condensation properly | Critical | 2026-07-19 15:58 | Work In Progress
WO-094 | 102 | Walls | wallpaper seams is separating | Medium | 2026-07-24 12:51 | Work In Progress
WO-095 | 306 | Floors | Bathroom Tiles Lose | Low | 2026-07-31 16:40 | Not Started
WO-096 | 104 | Technology | TV Remote Will Not Turn TV on or off. Update: Reprogramed Remote | Low | 2026-07-31 | Completed | Reprogramed Remote
| 306 | Technology | Not getting all channels and some channels are pixely | Medium | 2026-07-31 22:00 |  | Called TV company and got put on call back and have not heard nothing. 10:00PM Does it have the grey cable?

## Room Inspections
Detailed Room Inspections - Marriott Fairfield
Track room inspections, PM intervals, and follow-up status with a 30-day maintenance cycle.
Date | Room/Space | Inspection Status | HVAC | Plumbing | Electrical | Walls/Floors | Notes | Priority | Performed By | Last PM Date | Next Due Date | Days Remaining | PM Status
2026-07-17 | 210 | Follow-Up | OK | OK | Replace | Repair | Outlet needs to be replaced.Floor needs to be touched up in the bathroom.Walls and trim need to be repaired | High | Pablo | 2026-07-17 | 2026-08-16 | 16 | Current
2026-07-20 | 408 | Pass | OK | OK | OK | OK | Asthetic fix, cable management under desk. | Low | Pablo | 2026-07-20 | 2026-08-19 | 19 | Current
2026-07-20 | 101 | Follow-Up | OK | Replace | OK | Repair | Handheld shower head is leaking needs to be replaced , and the silicone needs to be redone on the top of the shower | Medium | Pablo | 2026-07-20 | 2026-08-19 | 19 | Current
2026-07-21 | 211 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-21 | 2026-08-20 | 20 | Current
2026-07-21 | 308 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-21 | 2026-08-20 | 20 | Current
2026-07-23 | 107 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 102 | Follow-Up | Repair | OK | OK | Repair | Wallpaper seams concealed better, clean and tab AC. | Medium | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 203 | Follow-Up | Repair | Repair | OK | OK | Touch up caulking in bathroom, clean and tab AC. | Medium | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 215 | Follow-Up | Repair | OK | OK | OK | Ac needs to be cleaned and tabbed. | Low | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 307 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 319 | Follow-Up | Repair | Repair | OK | OK | Readjust toilet actuator(Active WO-010), clean and tab AC. | Medium | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 411 | Follow-Up | Repair | OK | OK | OK | Ac needs to be cleaned and tabbed. | Low | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 415 | Follow-Up | Repair | OK | OK | OK | Ac needs to be cleaned and tabbed. | Low | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-23 | 419 | Follow-Up | Repair | OK | OK | OK | Ac needs to be cleaned and tabbed. | Low | Pablo | 2026-07-23 | 2026-08-22 | 22 | Current
2026-07-26 | 209 | Follow-Up | Repair | OK | Replace | OK | Repair thermostat, clean and tab AC, replace door battery. | High | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 217 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 219 | Follow-Up | OK | OK | Replace | OK | Door battery needs to be replaced. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 303 | Follow-Up | OK | OK | Replace | OK | Door battery needs to be replaced. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 304 | Follow-Up | OK | OK | Replace | OK | Door battery needs to be replaced, TV cable needs to be replaced, and missing window lock. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 306 | Follow-Up | OK | OK | Replace | OK | Door battery needs to be replaced, missing window lock. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 313 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 314 | Follow-Up | OK | OK | Replace | OK | TV cable needs to be replaced. | Low | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 318 | Follow-Up | OK | Repair | OK | OK | Multiple spots in bathroom need to be recaulked, missing window lock. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 319 | Follow-Up | OK | OK | Replace | OK | Door battery needs to be replaced. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 321 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 402 | Follow-Up | OK | OK | Replace | Repair | Door battery needs to be replaced, Tv cable needs to be replaced, towel hanger needs to be adjusted/repaired. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 415 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 417 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 104 | Pass | OK | OK | OK | OK | Nothing significant needs to be repaired or replaced. | Low | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 105 | Follow-Up | OK | OK | Replace | OK | Door battery needs to be replaced, missing window lock. | Critical | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
2026-07-26 | 206 | Follow-Up | OK | Repair | OK | OK | Multiple spots in bathroom need to be recaulked. | Medium | Pablo | 2026-07-26 | 2026-08-25 | 25 | Current
Formulas:
Next Due Date = IF([Last PM Date]="","",[Last PM Date]+30)
Days Remaining = IF([Next Due Date]="","",[Next Due Date]-TODAY())

## Parts Inventory
Parts Inventory
Manage critical spares, reorder triggers, vendors, and storage locations.
Part ID | Category | Part Name | Equipment/Area | Vendor | Unit Cost | On Hand | Min Level | Reorder Qty | Lead Time (Days) | Reorder Status | Critical Item | Storage Location | Notes

## Daily Tasks
Daily Maintenance Tasks
Use this sheet to manage daily building checks, hotel operations walk-throughs, and shift handoffs.
Task ID | Area | Task | Assigned To | Frequency | Due Day/Date | Est. Minutes | Status | Last Completed | Notes
D-001 | Boiler Room | Check boiler pressure, temperature, and leak points | AM Engineer | Daily | Every Day | 20 | Complete | 2026-07-16 | Document readings in log book
D-002 | Pool | Verify pool chemistry and equipment alarms | PM Engineer | Daily | Every Day | 15 | Complete | 2026-07-15 | Coordinate with front desk on closures
D-003 | Public Areas | Inspect lobby, corridors, and elevators for lighting or trip hazards | Shift Engineer | Daily | Every Day | 25 | Complete | 2026-07-15 | Open work order for deficiencies
D-004 | Exterior | Check parking lot, signage, and entry doors | Shift Engineer | Daily | Every Day | 15 | Complete | 2026-07-16 | Note weather-related issues

## Weekly Tasks
Weekly Maintenance Tasks
Use this sheet to plan recurring weekly preventive maintenance work.
Task ID | Area | Task | Assigned To | Frequency | Due Day/Date | Est. Minutes | Status | Last Completed | Notes
W-001 | Guest Rooms | Test sample of PTAC units and clean return grilles | HVAC Tech | Weekly | Monday | 90 | Not Started | 2026-07-09 | Rotate floors weekly
W-002 | Fire Safety | Test emergency lighting and exit signage | Electrician | Weekly | Tuesday | 60 | Complete | 2026-07-15 | Log failures for replacement
W-003 | Water Systems | Flush low-use fixtures and inspect for odor | Plumber | Weekly | Wednesday | 45 | In Progress | 2026-07-10 | Focus on out-of-order rooms
W-004 | Exterior | Inspect roof drains, downspouts, and grounds irrigation | Grounds/Maintenance | Weekly | Friday | 75 | Not Started | 2026-07-11 | Escalate ponding issues immediately

## Monthly Tasks
Monthly Maintenance Tasks
Use this sheet to track higher-touch preventive maintenance and inventory routines.
Task ID | Area | Task | Assigned To | Frequency | Due Day/Date | Est. Minutes | Status | Last Completed | Notes
M-001 | Life Safety | Inspect fire extinguishers and document seal/pressure status | Chief Engineer | Monthly | 1st Business Day | 75 | Not Started | 2026-06-30 | Coordinate with vendor if replacement is needed
M-002 | Guest Rooms | Deep inspection of 10% of rooms with furnishings checklist | Maintenance Supervisor | Monthly | 2nd Week | 180 | In Progress | 2026-06-20 | Use room inspection sheet for findings
M-003 | Inventory | Cycle count critical spares and update reorder points | Storeroom Clerk | Monthly | 3rd Week | 120 | Complete | 2026-07-02 | Match with purchasing records
M-004 | Mechanical | Lubricate motors, bearings, and door hardware | Shift Engineer | Monthly | Last Week | 150 | Not Started | 2026-06-26 | Record used materials

## Lists (hidden)
Dropdown Lists
Hidden lookup values used by the dashboard and operating sheets.
Inspection Status | System Status | Priority | Task Status | Critical Item
Pass | OK | Low | Not Started | Yes
Follow-Up | Repair | Medium | In Progress | No
Fail | Replace | High | Complete
|  | Critical | Deferred

## Room Inspection PM
Marriott Fairfield Room Inspection / PM
Printable guest-room inspection sheet tailored to Fairfield standards for guest-ready presentation, PM follow-up, and detailed corrective action tracking.
Date |  |  | Inspector
Property / Wing |  |  | Room / Floor
Room Type |  |  | Work Order
Occupancy |  |  | Status / Target
Inspection Item | Fairfield Standard | Result | Notes / Deficiencies | Corrective Action
General Room Readiness
Room presentation | Room is clean, odor-free, well-lit, and guest-ready with no visible clutter or trash.
Bedding and mattress | Linens are fresh, dry, tight, and free of stains or tears; mattress, box spring, and headboard are secure and clean.
Casegoods and upholstery | Desk, chair, nightstand, sofa, and other furniture are dust-free, stable, and free of chips, burns, stains, or loose hardware.
Windows and treatments | Windows, sheers, blackout curtains, and blinds open and close smoothly; fabric is clean and undamaged.
Closet and storage | Closet or wardrobe is clean and organized; hangers, luggage rack, and shelves are present and secure.
Brand amenities | Coffee maker, cups, ice bucket, hair dryer, safe, iron, and board are present and functional when equipped in the room type.
HVAC / Climate Control
PTAC or HVAC power | Unit powers on and responds correctly to the thermostat or control settings.
Heating and cooling | Heating and cooling modes produce strong, even airflow and reach set temperature without delay.
Filter and grille | Return grille, filter, and cabinet are clean, secured, and free of heavy dust build-up.
Noise and vibration | Unit runs quietly with no rattles, grinding, odor, or abnormal vibration.
Condensate and leaks | No water intrusion, condensate overflow, or staining is present around the unit.
Electrical / Lighting / Technology
Room lighting | Entry, bedside, desk, vanity, and bath lighting all operate correctly with working switches or dimmers.
Outlets and USB ports | All outlets, USB ports, and charging stations energize properly and are securely mounted.
GFCI protection | Bathroom and vanity GFCI outlets trip and reset properly; covers and faceplates are intact.
TV and remote | Television powers on, channels or streaming input work, and the remote operates correctly.
Telephone and connectivity | Room phone, data port, or posted Wi-Fi information is present and usable when applicable.
Cords and plugs | Power cords, plugs, and lamp wiring are undamaged, secured, and not creating a hazard.
Plumbing / Bathroom
Sink faucet and drain | Hot and cold water operate correctly, pressure is acceptable, and the sink drains without leaking or backing up.
Toilet operation | Toilet flushes, refills, and seats properly with no rocking, staining, or hidden leaks.
Tub or shower | Tub, shower, head, curtain or door, grout, caulk, and drain are clean, intact, and leak-free.
Vanity and mirror | Countertop, backsplash, mirror, sink basin, and vanity surfaces are clean and damage-free.
Exhaust fan | Bathroom fan vents properly and is free of excessive dust, noise, or damage.
Water temperature | Water temperature is consistent and acceptable at the sink and shower.
Plumbing leaks | No visible leaks are present under the sink, around the toilet, or at wall penetrations.
Walls / Ceiling / Trim
Walls and paint | Walls, wallpaper, and paint are free of holes, stains, peeling, scuffs, and visible patching issues.
Ceiling and vents | Ceiling, sprinkler escutcheons, diffusers, and vents are clean with no water marks or cracks.
Trim and caulk | Baseboards, corner beads, trim, and caulk lines are intact, sealed, and finished cleanly.
Artwork and mirrors | Artwork, mirrors, and décor are straight, secure, and free of chips, cracks, or fading.
Bathroom wall finish | Tile, grout, and wall finish in the bathroom are clean, sealed, and free of mold, mildew, or damage.
Floors / Baseboards / Thresholds
Floor surface | Carpet, tile, LVT/VCT, or other floor finish is clean, dry, and in good condition.
Floor damage | No burns, stains, cracks, lifted edges, loose tiles, or damaged seams are present.
Transitions and thresholds | Door thresholds, transitions, rugs, and mats are secure and do not create a trip hazard.
Baseboards and corners | Baseboards and corners are secure, clean, and free of gouges or separation.
Under furniture | Area under the bed, behind the door, and behind furniture is clean and free of debris.
Doors / Locks / Security
Entry door operation | Entry door closes, latches, and self-closes properly without binding or slamming.
Deadbolt and swing bar | Deadbolt, security latch, and related hardware function smoothly and securely.
Peephole and viewer | Peephole or viewer is clear, secure, and properly aligned.
Door seals and sweep | Door seals, sweep, hinges, frame, and closer are intact with no obvious light or sound gaps.
Bathroom and closet doors | Bathroom, closet, and connecting doors open, close, and latch properly.
Window and patio security | Window locks, secondary latches, and balcony or patio doors operate correctly when present.
Safety / Life Safety / Guest Security
Smoke detector | Smoke detector is present, unobstructed, and appears powered and functional.
Sprinkler head | Sprinkler head and escutcheon are unobstructed and free of damage or paint.
Emergency information | Emergency evacuation instructions, room phone info, and safety signage are present and legible.
Immediate hazards | No exposed wiring, broken glass, damaged outlets, or other immediate safety hazards are present.
Egress path | Primary exit path from the room is clear and unobstructed.
Final PM / Closeout
Deficiency log | All deficiencies are documented with the proper work order number or follow-up note.
Parts and materials | Parts, materials, or vendor support required for repair are identified and ordered if needed.
Room status | Room status is clearly marked as Ready, Follow-Up, or Out of Order.
Inspector sign-off | Inspector name, date, and supervisor review are completed before the room is returned to service.

## FLUSHMATE SNs
30075 Research Dr., New Hudson, MI 48165 |  |  |  |  | Site Information
Fax: |  |  |  |  | Contact: Pablo Chakone
Contact: |  |  |  |  | Company: Fairfield Inn & Suites
Address: 203 Outlet Dr., Hillsboro, TX 76645
Phone: (254) 582-8804
Email: fairfield.maint.203@gmail.com
Flushmate Serial Number Log
| Model # | Serial # |  | Install Date |  | Model # | Serial # |  | Install Date
101 |  | - | - | / / | 307 |  | - | - | / /
102 |  | - | - | / / | 308 |  | - | - | / /
103 |  | - | - | / / | 309 |  | - | - | / /
104 |  | - | - | / / | 310 |  | - | - | / /
105 |  | - | - | / / | 311 |  | - | - | / /
106 |  | - | - | / / | 313 |  | - | - | / /
107 |  | - | - | / / | 314 |  | - | - | / /
121 |  | - | - | / / | 315 |  | - | - | / /
201 |  | - | - | / / | 316 |  | - | - | / /
202 |  | - | - | / / | 317 |  | - | - | / /
203 |  | - | - | / / | 318 |  | - | - | / /
204 |  | - | - | / / | 319 |  | - | - | / /
205 |  | - | - | / / | 321 |  | - | - | / /
206 |  | - | - | / / | 401 |  | - | - | / /
207 |  | - | - | / / | 402 |  | - | - | / /
208 |  | - | - | / / | 403 |  | - | - | / /
209 |  | - | - | / / | 404 |  | - | - | / /
210 |  | - | - | / / | 405 |  | - | - | / /
211 |  | - | - | / / | 406 |  | - | - | / /
213 |  | - | - | / / | 407 |  | - | - | / /
214 |  | - | - | / / | 408 |  | - | - | / /
215 |  | - | - | / / | 409 |  | - | - | / /
216 |  | - | - | / / | 410 |  | - | - | / /
217 |  | - | - | / / | 411 |  | - | - | / /
218 |  | - | - | / / | 413 |  | - | - | / /
219 |  | - | - | / / | 414 |  | - | - | / /
221 |  | - | - | / / | 415 |  | - | - | / /
301 |  | - | - | / / | 416 |  | - | - | / /
302 |  | - | - | / / | 417 |  | - | - | / /
303 |  | - | - | / / | 418 |  | - | - | / /
304 |  | - | - | / / | 419 |  | - | - | / /
305 |  | - | - | / / | 421 |  | - | - | / /
306 |  | - | - | / / |  |  | - | - | / /